## Sheet1
Test Plan
1)Test Plan ID | Boots_WebApp_TP_0001
2)Objective | We are developing this test plan for health, beauty retailer & pharmacy chain namely "boots.com".This e-commerce site delivers the product to countries like Bangladesh, Ireland, and Italy. This site comprises User Interface & Admin Interface. User Interface could be accessed by the people throughout these countries mentioned & Admine Interface would be accessed by Boots authorized users.
3)Items To Be Tested | User Interface: i) Login, ii) Register
4)Testing Methodology | The methodology selected for this project could be: Iterative Development
5)Features To Be Tested | User Interface: i)New Customers could register through valid e-mail & other valid information ii) Old customers can sign in with the valid e-mail
6)Features Not To Be Tested | Admin Interface
7)Approach | Test Cases, Mind Map
8)Assumptions | i)Testers will get proper co-operations from developer team ii)Proper resource allocation will be given to the testers iii)Tester will get proper document to refer the CRS, FRS,FS & all those requirements.
9) Entry Criteria | i) Test Design Team formation, Responsibilities, Schedule, Requirements, Test Case Template, etc.. Training on Domain, Automation tools ii) Test Execution: Readiness of Test Lab Readiness of UAT Requirements Test Case docs Test Data Defect Report Template Etc
10)Exit Criteria | i)When 90% and above test cases are passed ii)Maximum defecs are fixed
11) Suspension Criteria | i)Supplier Issues ii)If resolving defects are more time consuming
12)Roles & Dependencies | 1)Test Manager: a)Resource Allocation, b)Having access to the Production Environment 2)Test Lead: a)Assigning Modules & features to be tested to each QA engineer,b)reviewing test cases,c)Approving test cases 3)Israth Jahan Nafi(QA Engineer): a)Understanding the requirements, b)Writing Test Scenarios, c)Writing Test cases, d)Getting these documents approved by the test Lead e)Test Execution f) Defect Tracking
13)Schedule | 1)1st November,2022: Collecting & Analyzing requirements, 2) 2nd-3rd Nov: Review meeting (I) 3)4th Nov: Generating Test Scenarios 4)5th Nov: Review meeting (II) 5)6th-15th Nov: Test Case Documentation 6)15th-17th Nov: Review Meeting (III) 7)18th-10th Nov: Test Data Collection 8)20th Nov: Review Meeting 9)21st Nov: Verifying test environment set up 10)22nd-23rd Nov: Create Test Batches 11) 24th-27th Nov: Evaluating exit criteria 12)28th Nov: Collecting all artifacts 13) 29th Nov: Test Summary Report
14)Training | N/A
15) Risk & Mitigation | i) Team members issues ii)Shortage of time iii)Budget
16) Test Environment | Application Type: Web Application, Internet, Public Windows Server 2016 UNIX server MS Exchange Server a) Web Server, b) EDP, c) Data storage Bugzilla Tool VSS MS Office Selenium Tool, etc…. Browser MS Edge Client-side: Windows 10 VSS MS Office Selenium Etc… AUT Environment .NET (C#, VC++, ADO) IIS -web server COM+ -App server SQL Server 2017 for Database server
17) Test Delivarables | i)Release Note ii)Test Plan iii)Review Report iv)Closed Defect Report v)Test Summary Report
18) Approvals | i)Test Plan Documentation: Israth Jahan Nafi(QA Engineer) ii)Elon Musk(QA Analyst) iii)Sundar Pichai(Project Manager)